**PROGRESS REPORT ON CAPITAL PROJECT 2010 TO 2013 BAYELSA STATE COMMAND**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ***S/N*** | ***LOTS NUMBER*** | ***PROJECT NUMBER*** | ***DESCRIPTION OF PROJECT*** | ***NAME OF CONTRACTOR*** | ***LOCATION*** | ***YEAR OF AWARD*** | **CONTRACT SUM** | ***STAGE OF WORK*** | **REMARKS** |
| *1* | *F-002031* | *NPF/FHQ/BYS/W/2010/01* | *REHABILITATION OF 1 NO 4 MAN R/F QUARTERS* | *OLORUNTOBA GLOBAL SERVICES* | *‘A’ DIVISION BARRACKS YENAGOA* | *YEAR 2010* | 8,093,978.60 | *CONTRACTOR REPORTED BUT WORK NOT COMMENCED* | ABANDONED |
| *2* | *F-002013* | *NPF/FHQ/BYS/W/2010/04* | *CONSTRUCTION OF 1 NO 3 BR INPRS QUARTERS* | *TONIBAU ENTER. LIMITED* | *OVOM YENAGOA* | *YEAR 2010* | *11,356,339.30* | *WORK AT ROOFING LEVEL* | ABANDONED |
| *3* | *F-002434* | *NPF/FHQ/W/2010/05* | *CONSTRUCTION OF 2 NO 4 R/F QUARTERS (STOREY BUILDING)* | *M/S TENAC NIG LTD* | *OVOM YENAGOA* | *YEAR 2010* | 112,215,001.79 | *WORK AT DPC* | ABANDONED |
| *4* | *F-002001* | *NPF/FHQ/W/2010/05* | *CONSTRUCTION OF 1 NO 3 BR INSPR QUARTERS.*  | *M/S TENAC NIG LTD* | *NEMBE* | *YEAR 2010* | 99,998,781.55 |  *1 NO 3 BR INSPRS YET TO COMMENCE* | ABANDONED |
| *5* | *F-007272* | *NPF/FHQ/W/2010/07* | *CONSTRUCTION OF ADMINISTRATION BLOCK STATE HEADQUARTERS* | *M/S MEGASTAR TECHNICAL & CONSTRUCTION LIMITED* | *KPANSIA YENAGOA* | *YEAR 2010* | 233,925,0224.52 | *REPORTED BUT THE LANDLORDS REFUSED ACCESS TO LAND UNTIL COMPENSATION CLAIMS ARE PAID* | ABANDONED |
| *6* | *F-002105* | *NPF/FHQ/W/2010/02* | *CONSTRUCTION OF 1 NO 4 MAN R/F QUARTERS (RAFT FOUNDATION)* | *M/S REALEST BUILDERS* | *OVOM YENAGOA* | *YEAR 2010* | 21,312,740.00 | *WORK ON DPC* | ABANDONED |
| ***7*** | ***F-111156*** | ***NPF/FHQ/W/BYS/2011/05*** | ***REHABILITATION OF 2 NO 8 MAN R/F QUARTERS***  | ***MR CHRIENAF NIG LTD*** | ***OVOM YENAGOA*** | ***2011*** | **47,320,949.21** | ***1 NO 8 MAN R/F ROOFED AND CEILED WHILE 1 NO. 8 MAN R/F YET TO COMMENCE*** | **DEMOLISHED BY STATE GOVT** |
| **8** | ***F-1305263*** | ***CW:0108/C/W/FHQ/ABJ/VOL.*** | ***CONSTRUCTION OF 2NO. 25 BEDS EACH, COTTAGE HOSPITAL BUNGALOW TYPE INCLUDING CONSTRUCTION OF 320M LINER METER FENCE (160M/EACH CLINIC)*** | ***M/S DAMAX INVESTMENT LIMITED*** | ***YENAGOA*** | **2013** | **183,333,333.33** | ***CONTRACTOR REPORTED , WORK NOT YET COMMENCED*** | ABANDONED |
| **9** | ***F-1305324*** | ***CW:0108/C/W/FHQ/ABJ/VOL.*** | ***CONSTRUCTION OF 1 NO. BLOCK OF 8 CLASSROOMS AT MARINE TRAINING SCHOOL*** | ***M/S BLUE FOUNTAIN PROPERTIES LTD*** | ***YENAGOA*** | **2013** |  | ***CONTRACTOR REPORTED, BUT WORK NOT COMMENCED*** | ***LAND NEWLY ACQUIRED AT EBEDBIRI*** |
| **10** | ***F-1305325*** | ***CW:0108/C/W/FHQ/ABJ/VOL.*** | ***CONSTRUCTIONB OF 2 NO. BLOCK OF 4 MAN RANK AND FILE QTRS 2 BEDROOM(STOREY BUILDING) WITH RAFT FOUNDATION AT MARINE TRAINING SCHOOL*** | ***M/S BLUE FUNDATION PROPERTIES LTD*** | ***YENAGOA*** | **2013** |  | ***CONTRACTOR REPORTED BUT WORK NOT COMMENCED*** | ***LAND YET TO BE ACQUIRED*** |
| **11** | ***F-1305329*** | ***CW:0108/C/W/FHQ/ABJ/VOL.*** | ***CONSTRUCTION OF 3000M LINEA METER BLOCK WALL FENCING WITH REINFORCED CONCRETE COLUMN,+WIRE AT MARINE TRAINING SCHOOL*** | ***M/S EVNORA INVESTMENT LTD*** | ***YENAGOA*** | **2013** |  | ***CONTRACTOR REPORTED BUT WORK NOT COMMENCED*** | ***LAND YET TO BE ACQUIRED AT EBEDBIRI*** |
| **12** | ***F-135330*** | ***CW:0108/C/W/FHQ/ABJ/VOL.*** | ***CONSTRUCTION OF 1 NO. ADMINISTRATIVE BLOCK (STOREY BUILDING) KUDAN TYPE INCLUDING FURNISHING AT MARINE TRAINING SCHOOL*** | ***M/S GEOTECH TECHNOLOGIES LTD*** | ***YENAGOA*** | ***2013*** |  | ***CONTRACTOR REPORTED, BUT WORK NOT COMMENCED*** | ***LAND NEWLY ACQUIRED AT EBEDBIRI*** |
| **13** | ***F-1305344*** | ***CW:0108/C/W/FHQ/ABJ./VOL.*** | ***CONSTRUCTION OF POLICE JETTY AT MARINE TRAINING SCHOOL*** | ***M/S GEOTECH TECHNOLOGIES LTD*** | ***YENAGOA*** | ***2013*** |  | ***CONTRACTOR REPORTED, BUT WORK NOT COMMENCED*** | ***LAND NEWLY ACQUIRED AT EBEDBIRI*** |
| **14** | *F-150016* | *NPF/FHQ/BYS/W/2015/01* | ***REHABILITATION OF 1 NO. 3 MAN RANK AND FILE QUARTERS***  | *GREENHILL GLOBAL CONCEPT LTD* | ***EKEKI, YENAGOA*** | ***2015*** | *9,001,642.50* | *WORK COMPLETED* | ***PAYMENT RECCOMMENDED*** |
| **15** | *F-180138*  | *NPF/FHQ/BYS/W/2018/01* | ***CONSTRUCTION OF MARINE POLICE POST***  | *SPECIALIZIED SOLUTION INC.* | ***OGBIA L.G.A*** | ***2018*** | *20,670,557.10* | *WORK COMMENCED* | ***WORK AT DPC LEVEL***  |

**DSP EBENUWA JOHN .I.**

 **STATE WORKS OFFICER**

 **BAYELSA STATER COMMAND**